## Gantt Chart - Tabla 1
GANTT CHART SAAS DIPASSIO |  |  | SAAS | [24 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | AI based SaaS |  |  |  |  | COMPANY NAME | [8 empty] | Dipassio SL
| PROJECT MANAGER | Ignacio B. Souto Jalón |  |  |  |  | DATE | [8 empty] | 2023-01-12
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter |  |  |  |  | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter Revisions |  |  |  |  | 100% | bar: WEEK 2 W
1.2 | Research |  |  |  |  | 90% | bar: WEEK 2 W to WEEK 3 W
1.3 | Projections |  |  |  |  | 40% | bar: WEEK 2 R to WEEK 3 R
1.4 | Stakeholders |  |  |  |  | 70% | bar: WEEK 3 M to WEEK 3 R
1.5 | Guidelines |  |  |  |  | 60% | bar: WEEK 3 T to WEEK 3 R
1.6 | Project Initiation |  |  |  |  | 50% | bar: WEEK 3 F
2 | Project Definition and Planning
2.1 | Scope & Goal Setting |  |  |  |  | 22% | bar: WEEK 4 M to WEEK 4 R
2.2 | Budget |  |  |  |  | 16% | bar: WEEK 4 F to WEEK 5 F
2.3 | Communication Plan |  |  |  |  | 0%
2.4 | Risk Management |  |  |  |  | 0%
3 | Project Launch & Execution
3.1 | Status & Tracking |  |  |  |  | 0%
3.2 | KPIs |  |  |  |  | 0%
3.2.1 | Monitoring |  |  |  |  | 0%
3.2.2 | Forecasts |  |  |  |  | 0%
3.3 | Project Updates |  |  |  |  | 0%
3.3.1 | Chart Updates |  |  |  |  | 0%
4 | Project Performance/Monitoring
4.1 | Project Objectives |  |  |  |  | 0%
4.2 | Quality Deliverables |  |  |  |  | 0%
4.3 | Effort & Cost Tracking |  |  |  |  | 0%
4.4 | Project Performance |  |  |  |  | 0%